Statement of Work

HOA Management SaaS Platform — MVP Build

Prepared: August 28, 2026  ·  Version 1.0  ·  Status: Draft for review

# 1. Project overview

This project delivers a multi-tenant, cloud-based HOA (homeowners association) management platform for the Philippine market, modeled on category leaders such as HOAS. The platform will be sold as SaaS to multiple independent HOAs, each operating as an isolated tenant on shared infrastructure.

The MVP scope prioritizes the features that make an HOA board switch to a new platform — accurate billing and accounting, homeowner and property records, and gate/visitor security — while deferring high-effort, adoption-dependent features (such as a resident marketplace) to a later phase.

## 1.1 Objectives

- Enable an HOA administrator to onboard a community, import properties and homeowners, and begin billing within a single session.

- Automate monthly dues billing with a correct, auditable double-entry ledger underneath.

- Give homeowners self-service visibility into their dues, balance, and payment history.

- Provide a guard-facing tool to validate visitor gate passes in real time.

- Support local payment methods relevant to the Philippine market (GCash, Maya, bank transfer, cash, check).

## 1.2 Out of scope for MVP

- Resident marketplace (buy/sell listings with buyer–seller messaging) — deferred to Phase 2, pending validated demand from live HOAs.

- RA 9904-compliant online voting and elections.

- Water metering and tiered utility billing.

- Amenity booking system.

- Native iOS/Android homeowner app (web-responsive portal only for MVP).

- Google Calendar sync and unified calendar.

# 2. Scope of work

## 2.1 Core platform & multi-tenancy

- Organization (tenant) model — each HOA is isolated by org_id across all data.

- Role-based access: platform super-admin, HOA admin/treasurer, board member, guard, homeowner.

- Authentication and session management.

## 2.2 Property & homeowner management

- Property database: unit number, type (residential/commercial/townhouse), monthly rate.

- Homeowner records linked to properties, including co-owners/renters.

- CSV import for initial onboarding of an HOA's property roll.

## 2.3 Billing & accounting

- Automated monthly dues invoice generation with configurable per-property-type rates.

- Manual payment recording — cash, check, bank transfer, GCash, Maya.

- Double-entry ledger: chart of accounts, journal entries, and journal lines auto-posted from invoice and payment events.

- Statement of Account (SOA) generation, single and bulk.

## 2.4 Homeowner portal

- View current dues, balance, and due dates.

- View payment history.

- View HOA announcements (read-only for MVP).

## 2.5 Gate security

- Guard-role portal for validating gate passes at entry.

- Single-use gate pass creation by admin or homeowner, with a validity window.

- Visitor log for the property.

## 2.6 Payments integration

- PayMongo integration covering both GCash and Maya as payment rails.

- Manual reconciliation view for offline payment methods (cash, check, bank transfer).

# 3. Deliverables

| Working software | Deployed multi-tenant web application covering all MVP scope in Section 2. |
| --- | --- |
| Source code | Full repository with commit history, handed over to client-owned version control. |
| Database schema | Documented schema (properties, billing, ledger, gate passes) with migration scripts. |
| Admin onboarding flow | Self-serve flow for a new HOA to sign up and begin configuration. |
| Documentation | Setup/deployment guide and a short admin user guide. |
| Test data | Seed script producing a representative demo HOA for QA and demos. |

# 4. Timeline & phases

Indicative timeline assuming one full-stack developer at typical velocity. Adjust based on actual team size and availability.

| Phase | Scope | Duration |
| --- | --- | --- |
| 1. Foundation | Multi-tenant data model, auth, org/admin setup | 1.5 weeks |
| 2. Property & billing core | Properties, homeowners, invoice generation, payment recording | 2 weeks |
| 3. Ledger | Chart of accounts, journal posting, SOA generation | 1.5 weeks |
| 4. Homeowner portal | Self-service dues/balance/payment history views | 1 week |
| 5. Gate security | Guard portal, gate pass creation & validation | 1 week |
| 6. Payments integration | PayMongo (GCash + Maya), manual reconciliation | 1 week |
| 7. QA & pilot onboarding | Bug fixing, first real HOA onboarded | 1.5 weeks |

Estimated total: ~9.5 weeks to MVP launch.

# 5. Assumptions & dependencies

- Client provides PayMongo (or equivalent PSP) merchant account credentials.

- Client provides at least one pilot HOA willing to onboard real data during Phase 7.

- Hosting/infrastructure costs (database, app hosting, domain) are billed separately from development effort.

- Legal/compliance review (Data Privacy Act RA 10173, RA 9904 where applicable) is the client's responsibility; this SOW covers technical implementation only, not legal certification.

- Marketplace and other Phase 2 features are explicitly excluded from MVP cost and timeline.

# 6. Acceptance criteria

- An HOA admin can sign up, create an org, import a property list, and generate the first month's dues invoices without developer assistance.

- A homeowner can log into the portal and see an accurate balance matching the underlying ledger.

- Every invoice and payment produces a balanced journal entry (debits = credits) verifiable via an audit query.

- A guard can validate a gate pass and see accept/reject status within 2 seconds.

- A GCash or Maya payment made through the portal is correctly reconciled to the corresponding invoice.

# 7. Sign-off

This Statement of Work represents the agreed scope for the MVP phase. Changes to scope will be handled via a written change order.

| Client signature |  |
| --- | --- |
| Date |  |
| Vendor signature |  |
| Date |  |